## Natty Schedule
Desktop Automated Testing – Schedule

Week	Date (Thursday)	Development Task	Development Release Milestone	Automated Test Schedule	Added	Count	Target	Comments
October 2010
1	October 21st	Toolchain Uploaded
2	October 28th	Developer Summit
November 2010
3	November 4th			Team Transition
4	November 11th
5	November 18th
6	November 25th	FeatureDefinitionFreeze				53
December 2010
7	December 2nd		Alpha 1			120
8	December 9th			Testing Sprint
9	December 16th			Mago Refactoring	16	136
10	December 23rd			Mago Refactoring	0	136
11	December 30th	DebianImportFreeze		Vacations
January 2011
12	January 6th			Mago Refactoring	32	168		New tests written with the mago-ng
13	January 13th	Ubuntu Platform & Linaro Rally
14	January 20th		10.04.2 Freeze	Merge of the tests written during the Rally. / + 49 Applications tests / + Automated Sanity Checks	130	298		Total Written: 319 / Total Running: / - Gnome: 298 / - Unity: 244
15	January 27th			Alacarte : 4 / Jockey : +1 / Empathy +3 / Unity: +1	9	307
February 2011
16	February 3rd		Alpha 2	ISO Testing
17	February 10th			Evolution Mailer: +5 / Software Center: +5 / Gwibber: +2 / User Admin : +3	0	307	15
18	February 17th		Ubuntu 10.04.2	ISO Testing
19	February 24th	FeatureFreeze		Evolution Mailer: +5 / Software Center: +5 / Chromium: +4 / User Admin: +1	0	307	15
March 2011
20	March 3rd		Alpha 3	ISO Testing
21	March 10th			Evolution Mailer: +10 / Software Center: +5 / Bugs found from Triage: +5	0	307	15	“Bugs found from triage” include : / - Reports from the DX Team for the Window Manager (Unity/Compiz) / - Regression Tests - / The associated bug report must be affected to the project 'Mago'
22	March 17th			Thunderbird Mailer: +10 / Bugs found from Triage: +5	0	307	15
23	March 24th	UserInterfaceFreeze, BetaFreeze		Thunderbird Mailer: +5 / Software-Properties: +2 / Language-support: +2 (Chinese & Asian languages) / Bugs found from Triage: +5	0	307	15
24	March 31st		Beta 1	ISO Testing
April 2011
25	April 7th	DocumentationStringFreeze		Bugs found from Triage: +15	0	307	15
26	April 14th	FinalFreeze, KernelFreeze, NonLanguagePackTranslationDeadline	Beta 2**	ISO Testing
27	April 21st	ReleaseCandidate, LanguagePackTranslationDeadline
28	April 28th	FinalRelease	Ubuntu 11.04

					Done	Target	Note: This is the number of tests running on the Gnome Desktop. The tests run on Unity is the same minus the “Application Menu” which are specific to the Gnome Desktop.
TOTAL					307	397

* List of the test cases

## Tests List
Count	Packages	Class	Method	Test
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Calculator
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Character Map
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Disk Usage Analyzer
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Passwords And Encryption Keys
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Take Screenshot
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Terminal
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open gedit Text Editor
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Tomboy Notes
1	Application Menu	Accessories.xml	ubuntu_menu.UbuntuMenuTest	Open Print Jobs
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	Import extended m3u
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	Import extended pls
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	Import simple m3u
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	Import simple pls
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	Add Podcast
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	Miro
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	SmartPlayList
1	banshee-1	banshee_tests.xml	banshee_tests.Banshee_Tests	Play File
1	baobab	baobab_scans.xml	baobab_scans.BaobabScans	Scan_Folder
1	baobab	baobab_scans.xml	baobab_scans.BaobabScans	Scan_Home_Directory
1	baobab	baobab_scans.xml	baobab_scans.BaobabScans	Scan_Filesystem
1	brasero	brasero_basics.xml	brasero_basics.BraseroBasics	Burn Data ISO
1	computer-janitor-gtk	computer_janitor_gtk_basics.xml	computer_janitor_gtk_basics.Computer_janitor_gtkBasics	about_dialog
1	evolution indicator	evolution_indicator.xml	evolution_indicator.EvolutionIndicatorTest	IndicatorShowsTest
1	evolution indicator	evolution_indicator.xml	evolution_indicator.EvolutionIndicatorTest	BasicSendAndIndicationTest
1	evolution indicator	evolution_indicator.xml	evolution_indicator.EvolutionIndicatorTest	IndicatorShowsTest
1	evolution	evolution_messaging.xml	evolution_messaging.EvolutionUseTest	BasicSendTest
1	evolution	evolution_notify.xml	evolution_notify.EvolutionNotifyTest	BasicSendTestAndNotification
1	firefox	firefox_basics.xml	firefox_basics.FirefoxBasics	open_url
1	firefox	firefox_basics.xml	firefox_basics.FirefoxBasics	search_google
1	firefox	firefox_basics.xml	firefox_basics.FirefoxBasics	play_with_tabs
1	firefox	firefox_basics.xml	firefox_basics.FirefoxBasics	bookmarks
1	Application Menu	Games.xml	ubuntu_menu.UbuntuMenuTest	Open AisleRiot Solitaire
1	Application Menu	Games.xml	ubuntu_menu.UbuntuMenuTest	Open Mahjongg
1	Application Menu	Games.xml	ubuntu_menu.UbuntuMenuTest	Open Mines
1	Application Menu	Games.xml	ubuntu_menu.UbuntuMenuTest	Open Sudoku
1	Application Menu	Games.xml	ubuntu_menu.UbuntuMenuTest	Open gbrainy
1	gbrainy	gbrainy_basics.xml	gbrainy_basics.GbrainyBasics	about_dialog
1	gcalctool	gcalctool_calculations.xml	gcalctool_calculations.GCalctoolCalculations	1
1	gcalctool	gcalctool_calculations.xml	gcalctool_calculations.GCalctoolCalculations	2
1	gcalctool	gcalctool_calculations.xml	gcalctool_calculations.GCalctoolCalculations	3
1	gcalctool	gcalctool_calculations.xml	gcalctool_calculations.GCalctoolCalculations	4
1	gcalctool	gcalctool_calculations.xml	gcalctool_calculations.GCalctoolCalculations	5
1	gcalctool	gcalctool_calculations.xml	gcalctool_calculations.GCalctoolCalculations	6
1	gcalctool	gcalctool_calculations.xml	gcalctool_calculations.GCalctoolCalculations	7
1	gcalctool	gcalctool_options.xml	gcalctool_options.GCalctoolOptions	Show Thousands Operator
1	gcalctool	gcalctool_views.xml	gcalctool_views.GCalctoolViews	Advanced
1	gcalctool	gcalctool_views.xml	gcalctool_views.GCalctoolViews	Financial
1	gcalctool	gcalctool_views.xml	gcalctool_views.GCalctoolViews	Programming
1	gcalctool	gcalctool_views.xml	gcalctool_views.GCalctoolViews	Basic
1	gedit	gedit_chains.xml	gedit_chains.GEditChain	Unicode Tests
1	gedit	gedit_chains.xml	gedit_chains.GEditChain	ASCII Test
1	seahorse	generate_pgp.xml	generate_pgp.SeahorsePGP	Generate PGP
1	seahorse	generate_ssh.xml	generate_ssh.SeahorseSSH	Generate SSH
1	gnome-about-me	gnome_about_me_tests.xml	gnome_about_me_tests.GnomeAboutMeTests	Change Text Values
1	gnome-about-me	gnome_about_me_tests.xml	gnome_about_me_tests.GnomeAboutMeTests	Change Picture to PNG
1	gnome-about-me	gnome_about_me_tests.xml	gnome_about_me_tests.GnomeAboutMeTests	Change Picture to SVG
1	gnome-about-me	gnome_about_me_tests.xml	gnome_about_me_tests.GnomeAboutMeTests	Clean up values
1	gnome-appearance-properties	gnome_appearance_properties.xml	gnome_appearance_properties.GnomeAppearancePropertiesTests	Change GTK Theme
1	gnome-appearance-properties	gnome_appearance_properties.xml	gnome_appearance_properties.GnomeAppearancePropertiesTests	Change Window Border
1	gnome-appearance-properties	gnome_appearance_properties.xml	gnome_appearance_properties.GnomeAppearancePropertiesTests	Change Icon Theme
1	gnome-appearance-properties	gnome_appearance_properties.xml	gnome_appearance_properties.GnomeAppearancePropertiesTests	Change Pointer Theme
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	test_ping
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	test_traceroute
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	test_portscan
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	test_whois
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	netstat_routing
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	netstat_activeservices
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	netstat_multicast
1	gnome-nettool	gnome_nettool_basics.xml	gnome_nettool_basics.Gnome_nettoolBasics	about_dialog
1	gnome-search-tool	gnome_search_tool_tests.xml	gnome_search_tool_tests.Gnome_search_toolTests	UTF8 Search
1	gnome-search-tool	gnome_search_tool_tests.xml	gnome_search_tool_tests.Gnome_search_toolTests	Search RTL Hebrew
1	gnome-search-tool	gnome_search_tool_tests.xml	gnome_search_tool_tests.Gnome_search_toolTests	Search RTL Arabic
1	gnome-search-tool	gnome_search_tool_tests.xml	gnome_search_tool_tests.Gnome_search_toolTests	Search with wildcard
1	gnome-search-tool	gnome_search_tool_tests.xml	gnome_search_tool_tests.Gnome_search_toolTests	Search on Filesystem
1	gnome-search-tool	gnome_search_tool_tests.xml	gnome_search_tool_tests.Gnome_search_toolTests	Enable all options
1	gnome-sound-recorder	gnome_sound_recorder_basics.xml	gnome_sound_recorder_basics.Gnome_sound_recorderBasics	about_dialog
1	gnome-sudoku	gnome_sudoku_basics.xml	gnome_sudoku_basics.Gnome_sudokuBasics	about_dialog
1	gnome-system-log	gnome_system_log_tests.xml	gnome_system_log_tests.Gnome_system_logTests	expand_logs
1	gnome-system-log	gnome_system_log_tests.xml	gnome_system_log_tests.Gnome_system_logTests	check_logs
1	gnome-system-log	gnome_system_log_tests.xml	gnome_system_log_tests.Gnome_system_logTests	zoom_levels
1	gnome-system-log	gnome_system_log_tests.xml	gnome_system_log_tests.Gnome_system_logTests	about_dialog
1	gnome-system-monitor	gnome_system_monitor_tests.xml	gnome_system_monitor_tests.Gnome_system_monitorTests	process_preferences
1	gnome-system-monitor	gnome_system_monitor_tests.xml	gnome_system_monitor_tests.Gnome_system_monitorTests	filesystem_preferences
1	gnome-system-monitor	gnome_system_monitor_tests.xml	gnome_system_monitor_tests.Gnome_system_monitorTests	change_views
1	gnome-system-monitor	gnome_system_monitor_tests.xml	gnome_system_monitor_tests.Gnome_system_monitorTests	change_process_sorting
1	gnome-system-monitor	gnome_system_monitor_tests.xml	gnome_system_monitor_tests.Gnome_system_monitorTests	search_open_files
1	gnome-terminal	gnome_terminal_basics.xml	gnome_terminal_basics.Gnome_terminalBasics	about_dialog
1	gnomine	gnomine_basics.xml	gnomine_basics.GnomineBasics	about_dialog
1	gobby	gobby_basics.xml	gobby_basics.GobbyBasics	about_dialog
1	gucharmap	gucharmap_basics.xml	gucharmap_basics.GucharmapBasics	about_dialog
1	indicator-applet	indicator_applet.xml	indicator_applet.IndicatorAppletTest	Server
1	indicator-applet	indicator_applet.xml	indicator_applet.IndicatorAppletTest	MessageIndicator
1	indicator-applet	indicator_applet.xml	indicator_applet.IndicatorAppletTest	IconChange
1	indicator-applet	indicator_applet.xml	indicator_applet.IndicatorAppletTest	DisplayIndicator
1	indicator-applet	indicator_applet.xml	indicator_applet.IndicatorAppletTest	DisplayServer
1	Application Menu	Internet.xml	ubuntu_menu.UbuntuMenuTest	Open Firefox
1	Application Menu	Internet.xml	ubuntu_menu.UbuntuMenuTest	Open Terminal Server Client
1	Application Menu	Internet.xml	ubuntu_menu.UbuntuMenuTest	Open Transmission BitTorrent Client
1	mahjongg	mahjongg_basics.xml	mahjongg_basics.MahjonggBasics	about_dialog
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_move_to_trash
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_empty_trash
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_hidden_files
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	zoom_in
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	change_views
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_add_bookmark
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_remove_bookmark
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	arrange_by
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_toolbars
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_ftp
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_ssh
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_webdav
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	test_preferences
1	nautilus	nautilus_basics.xml	nautilus_basics.NautilusBasics	about_dialog
1	notify-osd	notify_osd.xml	notify_osd.NotifyOSDTest	IconSummaryBody
1	notify-osd	notify_osd.xml	notify_osd.NotifyOSDTest	IconSummary
1	notify-osd	notify_osd.xml	notify_osd.NotifyOSDTest	SummaryBody
1	notify-osd	notify_osd.xml	notify_osd.NotifyOSDTest	Summary
1	notify-osd	notify_osd.xml	notify_osd.NotifyOSDTest	Queue
1	notify-osd	notify_osd.xml	notify_osd.NotifyOSDTest	Synchronous
1	office	Office.xml	ubuntu_menu.UbuntuMenuTest	Open Evolution Mail
1	soffice	ooffice_basics.xml	ooffice_basics.OofficeBasics	Launch Spreadsheet Application
1	soffice	ooffice_basics.xml	ooffice_basics.OofficeBasics	Launch Document Application
1	soffice	ooffice_basics.xml	ooffice_basics.OofficeBasics	Launch Presentation Application
1	soffice	ooffice_basics.xml	ooffice_basics.OofficeBasics	Launch Drawing Application
1	palimpsest	palimpsest_basics.xml	palimpsest_basics.PalimpsestBasics	about_dialog
1	pitivi	pitivi_basics.xml	pitivi_basics.PitiviBasics	about_dialog
1	shotwell	shotwell_basics.xml	shotwell_basics.ShotwellBasics	Import Folder Copy
1	shotwell	shotwell_basics.xml	shotwell_basics.ShotwellBasics	Import Folder Link
1	shotwell	shotwell_basics.xml	shotwell_basics.ShotwellBasics	DoesMenuItemExists
1	simple-scan	simple_scan.xml	simple_scan.Simple_scan	Text Scan test
1	simple-scan	simple_scan.xml	simple_scan.Simple_scan	Photo Scan test
1	software-center	software_center.xml	software_center.Software_center	Search Software
1	software-center	software_center.xml	software_center.Software_center	Install Software
1	software-center	software_center.xml	software_center.Software_center	Remove Software
1	sol	sol_basics.xml	sol_basics.SolBasics	about_dialog
1	Application Menu	SoundVideo.xml	ubuntu_menu.UbuntuMenuTest	Open Brasero
1	Application Menu	SoundVideo.xml	ubuntu_menu.UbuntuMenuTest	Open Movie Player
1	Application Menu	SoundVideo.xml	ubuntu_menu.UbuntuMenuTest	Open Rhythmbox Music Player
1	Application Menu	SoundVideo.xml	ubuntu_menu.UbuntuMenuTest	Open Sound Recorder
1	Application Menu	SoundVideo.xml	ubuntu_menu.UbuntuMenuTest	Open Pitivi Video Editor
1	system-config-printer	system_config_printer_basics.xml	system_config_printer_basics.System_config_printerBasics	about_dialog
1	gnome-screenshot	take_screenshot.xml	take_screenshot.TakeScreenshot	Grab Desktop
1	gnome-screenshot	take_screenshot.xml	take_screenshot.TakeScreenshot	Grab Window
1	gnome-screenshot	take_screenshot.xml	take_screenshot.TakeScreenshot	Grab Area
1	unity	test_decorations.py	TestUnityDecorations	focusedbutton_LP704413
1	empathy	test_empathy.py	EmpathyTests	01_account_assistant
1	empathy	test_empathy.py	EmpathyTests	02_general_preferences
1	empathy	test_empathy.py	EmpathyTests	03_notifications_preferences
1	gnome-terminal	test_gnome-terminal.py	TerminalTests	01_add_new_profile
1	gnome-terminal	test_gnome-terminal.py	TerminalTests	02_delete_profile
1	gnome-terminal	test_gnome-terminal.py	TerminalTests	03_zoom_out
1	gnome-terminal	test_gnome-terminal.py	TerminalTests	04_zoom_in
1	gnome-terminal	test_gnome-terminal.py	TerminalTests	05_open_new_tabs
1	gnome-terminal	test_gnome-terminal.py	TerminalTests	06_close_tabs
1	jockey-gtk	test_jockey-gtk.py	JockeyTests	help_button
1	jockey-gtk	test_jockey-gtk.py	JockeyTests	activate_is_active
1	gnome-language-selector	test_languageselector.py	TestLanguageSelector	01InstallLanguage
1	gnome-language-selector	test_languageselector.py	TestLanguageSelector	02RemoveLanguage
1	soffice	test_OOo.py	TestOOo	01MainMenu
1	soffice	test_OOo.py	TestOOo	02Writer
1	soffice	test_OOo.py	TestOOo	03Calc
1	soffice	test_OOo.py	TestOOo	04Impress
1	soffice	test_OOo.py	TestOOo	05Draw
1	evince	test_opendocument.py	TestEvince	open_bmp
1	evince	test_opendocument.py	TestEvince	open_cb7
1	evince	test_opendocument.py	TestEvince	open_cbr
1	evince	test_opendocument.py	TestEvince	open_cbt
1	evince	test_opendocument.py	TestEvince	open_cbz
1	evince	test_opendocument.py	TestEvince	open_djvu
1	evince	test_opendocument.py	TestEvince	open_dvi
1	evince	test_opendocument.py	TestEvince	open_eps
1	evince	test_opendocument.py	TestEvince	open_gif
1	evince	test_opendocument.py	TestEvince	open_jpg
1	evince	test_opendocument.py	TestEvince	open_pdf
1	evince	test_opendocument.py	TestEvince	open_pdfbz2
1	evince	test_opendocument.py	TestEvince	open_pdfgz
1	evince	test_opendocument.py	TestEvince	open_png
1	evince	test_opendocument.py	TestEvince	open_pnm
1	evince	test_opendocument.py	TestEvince	open_ps
1	evince	test_opendocument.py	TestEvince	open_tif
1	evince	test_opendocument.py	TestEvince	open_tiff
1	evince	test_opendocument.py	TestEvince	open_xpm
109	Sanity Checks – Desktop apps with a .dekstop file			Launch/Close or Launch/About/Close
1	shotwell	test_shotwell.py	TestShotwell	import_from_folder_copy
1	shotwell	test_shotwell.py	TestShotwell	import_from_folder_link
1	shotwell	test_shotwell.py	TestShotwell	add_and_remove_tags
1	shotwell	test_shotwell.py	TestShotwell	filter_by_rating
1	shotwell	test_shotwell.py	TestShotwell	export
1	shotwell	test_shotwell.py	TestShotwell	import_from_fspot
1	shotwell	test_shotwell.py	TestShotwell	metadata
1	time-admin	test_timeadmin.py	TestTimeAdmin	01checktime
1	time-admin	test_timeadmin.py	TestTimeAdmin	02changetime
1	time-admin	test_timeadmin.py	TestTimeAdmin	03changetimezone
1	totem	test_totem.py	TotemTests	01_general_preferences
1	totem	test_totem.py	TotemTests	02_display_preferences
1	totem	test_totem.py	TotemTests	03_audio_preferences
1	totem	test_totem.py	TotemTests	04_plugins
1	totem	test_totemplayback.py	TestTotem	totem_audio_playback
1	transmission-gtk	test_transmission.py	TestTransmission	Add torrent
1	transmission-gtk	test_transmission.py	TestTransmission	Download torrent
1	transmission-gtk	test_transmission.py	TestTransmission	Remove torrent
1	tomboy	tomboy_basics.xml	tomboy_basics.TomboyBasics	about_dialog
1	tomboy	tomboy_basics.xml	tomboy_basics.TomboyBasics	create note and delete it
1	totem	totem_basics.xml	totem_basics.TotemBasics	Check audio playback
1	tsclient	tsclient_basics.xml	tsclient_basics.TsclientBasics	about_dialog
1	unity	unity.xml	unity.UnityTest	fullscreen_evince
1	update-manager	update_manager.xml	update_manager.UpdateManagerTest	Unselect All
1	update-manager	update_manager.xml	update_manager.UpdateManagerTest	Update None
1	update-manager	update_manager.xml	update_manager.UpdateManagerTest	Update First
1	vinagre	vinagre_basics.xml	vinagre_basics.VinagreBasics	about_dialog
1	windowmanager	windowmanager.xml	windowmanager.WindowManagerTest	Maximize/Restore Window (gedit)
1	windowmanager	windowmanager.xml	windowmanager.WindowManagerTest	Maximize/Restore Window (mahjongg)
1	windowmanager	windowmanager.xml	windowmanager.WindowManagerTest	Maximize/Restore Window (Ubuntu Software Center)
1	xchat	xchat_basics.xml	xchat_basics.XchatBasics	about_dialog
1	yelp	yelp_basics.xml	yelp_basics.YelpBasics	about_dialog
323	Total Written

1	gwibber			Preferences
2	gwibber			Add/Remove Account
	ubuntuone
1	chromium-browser			open_url
1	chromium-browser			search_google
1	chromium-browser			play_with_tabs
1	chromium-browser			bookmarks
1	Software-center			sc-01 – Follow the link
1	Software-center			Test case: (sc-004) From the top-level “Get Software” screen, search for “atom
1	Software-center			Test case: (sc-005) Navigate to “Get Software” > “Fonts”. Select “A Lee’s free Hangul TrueType fonts (ttf-alee)”
1	Software-center			Test case: (sc-006) In the “Get Software” section, navigate to the AbiWord application, and scroll to the bottom of the AbiWor
1	Software-center			Test case: (sc-007) In the “Installed Software” section, navigate to the Firefox application. Close the Center, then reopen it. Click on “Installed Software”. The Center should display the top level of the Installed Software section.
1	Software-center			Test case: (sc-009) Back/Forward Navigation
1	Software-center			Test case: (sc-010) Keyboard navigation
1	Software-center			Test case: (sc-011) Search
1	Software-center			Test case: (sc-013) Treeview Collapse/Expand
1	Software-center			Test case: (sc-015) Search for the “backintime-gnome” package. The item should have the title “Back In Time (backintime-gnome)”
1	Software-center			Test case: (sc-016) Mulitple package search
	Software-center / Other			Reviews
	Software-center / Other			Purchase
1	Software-properties-gtk			Disable canonical partner and fetch fluendo
1	Software-properties-gtk			Enable a additional repository (to be defined)
2	gnome-language-selector			Enable Chinese/Disable Chinese
2	Users-admin			Add/Remove/Edit groups
3	Users-admin			Add/Remove/Edit users + Add user to a group
4	alacarte			Add/Remove/Modify/Enable/Disable entry
2	evolution mailer			Send Mail / With Attachment	x
2	evolution mailer			Forward/Reply Mail
2	evolution mailer			Change properties of a Mail (read/unread, junk/unjunk)
1	evolution mailer			Save draft
6	evolution mailer			Copy / Move / Delete Mail (Local ↔ Server)
2	evolution mailer			Create Folder
8	evolution mailer			Copy / Move / Delete / Rename Folder (Local and Server)
1	evolution mailer			Create Filter
1	evolution mailer			Create vFolder
1	evolution mailer			Search for Mail
4	evolution mailer			Offline operations
1	evolution mailer			Search in Mail
	evolution mailer			Additional test cases at http://www.go-evolution.org/Mailer_Automation
2	thunderbird mail			Send Mail / With Attachment
2	thunderbird mail			Forward/Reply Mail
2	thunderbird mail			Change properties of a Mail (read/unread, junk/unjunk)
1	thunderbird mail			Save draft
6	thunderbird mail			Copy / Move / Delete Mail (Local ↔ Server)
2	thunderbird mail			Create Folder
8	thunderbird mail			Copy / Move / Delete / Rename Folder (Local and Server)
1	thunderbird mail			Create Filter
1	thunderbird mail			Create vFolder
1	thunderbird mail			Search for Mail
4	thunderbird mail			Offline operations
1	thunderbird mail			Search in Mail

	Additional Tests found from Bug Triage activity

93

416	Grand Total